|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL ONE  *Chair (or Lead): Brother ABC* | | | Details of goal! | | | | | |
| **Action Steps** | **Timeline** | **Coordinator** | | | **Participants** | | **External Support** | **Resources** |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |
|  |  |  | | |  | |  |  |

**EXAMPLE** (just the first 6 months of a 12 month project)

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL EIGHT  *Chair (or Lead): Brother ABC* | | | Create an educational foundation supported by an annual scholarship luncheon | | | | | |
| **Action Steps** | **Timeline** | **Coordinator** | | | **Participants** | | **External Support** | **Resources** |
| Establish foundation and scholarship luncheon committee | September 2016 | Brother A | | | Brother Z | | The Georgia Center for Nonprofits | hwww.gcn.org |
| Determine scholarship luncheon theme | October 2016 | Brother B | | | Scholarship luncheon committee | |  |  |
| Build scholarship luncheon budget | October 2016 | Brother C | | | Chapter Treasurer | |  |  |
| Identify three possible venues to visit | October 2016 | Brother C | | | Brother A | |  |  |
| Select scholarship luncheon date and location | October 2016 | Brothers A and C | | | Scholarship luncheon committee | |  |  |
| Select scholarship luncheon speaker | November 2016 | Brother A | | | Scholarship luncheon committee | |  |  |
| Determine luncheon menu | November 2016 | Brother D | | | Scholarship luncheon committee | | Hotel A Staff |  |
| Solicit commemorative program book advertisements | November 2016-February 2017 | Brother E | | | Brothers | | Hillside Print Shop, Joyce Motley mottley@hillsidechapel.org |  |